## Sheet1
Tracker Owner - Pranav (AYLIEN)
| Priority Codes | High - high impact - needs to be addressed
Medium - workarounds available
Low - just a question at this stage
Item | Category | Description (of request / action) | Status | Status Update | WF Priority | Who at WF? | Who at Aylien? | What? | When?
1 | Alexa data | Alexa data to be updated - initially in a file format. | Closed | Completed | Medium |  | Susan | Will to deliver a file | by week ending Mar. 13th
2 | Environmental query | Will and Aaron/Will/ Zach to identify an appropriate query to identify climate change news. As a starting point you may wish to start with the top level "environmental issue" label 06000000. This will include issues which aren't necessarily climate change related but you can identify the labels that aren't relevant in your results and exclude them. | Open | 09 Mar. - Query sent with suggested taxonomy. Waiting for WF feedback | Medium |  | Will Rees | Will to discuss best categories to use for environmental stories. | by week ending Mar. 13th
3 | Regulatory Sources | WF to send of a list of regulatory sources to add to the News API. Aylien to review and see if they are RSS feeds or require scrapping. | Open |  | Medium | WF to Send | Pranav | Assess sources for complexity to add. | by week ending Mar. 13th
4 | Clusering Session | Set up a demo session - discuss WF requirements. See if AYLIEN clustering is a good fit. | Open |  | Medium |  | Will Rees | Demo | Agree time for week beginning Mar. 16th
5 | Dropped Sources | Bloomberg is a source that was available during WF testing but not currently available on the AYLIEN News API. | Open | Status detailed in email | High |  | Roy | Check if this source can be supported via the API | by week ending May 01
6 | Source Request | Check availability/possibility to add list of sources shared by Aaron | Open | Ongoing | Medium |  | Roy